## Sheet1
Hypothetical Project Cost - Budget vs. Actual
[5 empty] | Budget Hours | [6 empty] | Actual Hours | [6 empty] | Budget Cost | [6 empty] | Actual Cost
| Project | Task | Resource | Cost $ / hr | Bud hrs Mth1 | Bud hrs Mth2 | Bud hrs Mth3 | Bud hrs Mth4 | Bud hrs Mth5 | Bud hrs Mth6 | Total Budget hours | Act hrs Mth1 | Act hrs Mth2 | Act hrs Mth3 | Act hrs Mth4 | Act hrs Mth5 | Act hrs Mth6 | Total Actual hours | Bud Cst Mth1 | Bud Cst Mth2 | Bud Cst Mth3 | Bud Cst Mth4 | Bud Cst Mth5 | Bud Cst Mth6 | Total Budgetted Cost | Act Cst Mth1 | Act Cst Mth2 | Act Cst Mth3 | Act Cst Mth4 | Act Cst Mth5 | Act Cst Mth6 | total Actual cost
| Project A | AT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 24 | 24 | 24 | 30 | 30 | 30 | 162 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 6000 | 1200 | 1200 | 1200 | 1500 | 1500 | 1500 | 8100
| Project A | AT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 80 | 80 | 80 | 90 | 90 | 90 | 510 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 16800 | 2800 | 2800 | 2800 | 3150 | 3150 | 3150 | 17850
| Project A | AT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 18000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 18000
| Project A | AT1 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 12600 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 12600
| Project A | AT1 | Jim | 90 | 140 | 140 | 140 | 140 | 140 | 140 | 840 | 160 | 160 | 160 | 160 | 160 | 160 | 960 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600 | 75600 | 14400 | 14400 | 14400 | 14400 | 14400 | 14400 | 86400
| Project A | AT2 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 500 | 500 | 500 | 500 | 500 | 500 | 3000
| Project A | AT2 | Monique | 105 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 12600 | 2100 | 2100 | 2100 | 2100 | 2100 | 2100 | 12600
| Project A | AT3 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 6000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 6000
| Project A | AT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600
| Project B | BT1 | Gail | 50 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 24 | 24 | 24 | 24 | 24 | 24 | 144 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 6000 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200
| Project B | BT1 | Jenny | 75 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 50 | 50 | 50 | 50 | 50 | 50 | 300 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 18000 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 22500
| Project B | BT1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600
| Project B | BT2 | Gail | 50 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 250 | 250 | 250 | 250 | 250 | 250 | 1500 | 250 | 250 | 250 | 250 | 250 | 250 | 1500
| Project B | BT2 | Monique | 105 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 25200 | 4200 | 4200 | 4200 | 4200 | 4200 | 4200 | 25200
| Project B | BT2 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 50 | 50 | 50 | 25 | 25 | 25 | 225 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 33600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 31500
| Project B | BT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600
| Project B | BT3 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000
| Project B | BT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 50 | 50 | 50 | 25 | 25 | 25 | 225 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 33600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 31500
| Project C | CT1 | Gail | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 5 | 5 | 5 | 5 | 5 | 5 | 30 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 250 | 250 | 250 | 250 | 250 | 250 | 1500
| Project C | CT1 | Tom | 35 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 16800 | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | 16800
| Project C | CT1 | Jenny | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 36000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 36000
| Project C | CT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000
| Project C | CT2 | Monique | 105 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 120 | 120 | 120 | 120 | 120 | 120 | 720 | 8400 | 8400 | 8400 | 8400 | 8400 | 8400 | 50400 | 12600 | 12600 | 12600 | 12600 | 12600 | 12600 | 75600
| Project C | CT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600
| Project C | CT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000
| Project C | CT3 | Gail | 50 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000
| Project C | CT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600
| Project C | CT3 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 50 | 50 | 50 | 25 | 25 | 25 | 225 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 33600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 31500
| Project C | CT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600
| Project C | CT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000
| Project C | CT5 | Erica | 140 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 50 | 50 | 50 | 25 | 25 | 25 | 225 | 5600 | 5600 | 5600 | 5600 | 5600 | 5600 | 33600 | 7000 | 7000 | 7000 | 3500 | 3500 | 3500 | 31500
| Project C | CT5 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600
| Project D | DT1 | Jim | 90 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 15 | 15 | 15 | 15 | 15 | 15 | 90 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 | 10800 | 1350 | 1350 | 1350 | 1350 | 1350 | 1350 | 8100
| Project D | DT1 | Inigo | 95 | 160 | 160 | 160 | 160 | 160 | 160 | 960 | 110 | 110 | 110 | 110 | 110 | 110 | 660 | 15200 | 15200 | 15200 | 15200 | 15200 | 15200 | 91200 | 10450 | 10450 | 10450 | 10450 | 10450 | 10450 | 62700
| Project D | DT1 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000
| Project D | DT1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600
| Project D | DT2 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 36000 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 36000
| Project D | DT2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600
| Project D | DT2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000
| Project D | DT2 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600
| Project D | DT3 | Sarah | 75 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 90 | 90 | 90 | 90 | 90 | 90 | 540 | 6000 | 6000 | 6000 | 6000 | 6000 | 6000 | 36000 | 6750 | 6750 | 6750 | 6750 | 6750 | 6750 | 40500
| Project D | DT3 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600
| Project D | DT3 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600
| Project D | DT4 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600
| Project D | DT4 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000
| Project D | DT4 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600
| Project E | ET1 | Gail | 50 | 40 | 40 | 40 | 40 | 40 | 40 | 240 | 50 | 50 | 50 | 50 | 50 | 50 | 300 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 12000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 15000
| Project E | ET1 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600
| Project E | ET1 | Crystal | 120 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 30 | 30 | 30 | 30 | 30 | 30 | 180 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600 | 3600 | 3600 | 3600 | 3600 | 3600 | 3600 | 21600
| Project E | ET2 | Sondra | 45 | 160 | 160 | 160 | 160 | 160 | 160 | 960 | 160 | 160 | 160 | 160 | 160 | 160 | 960 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 43200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 43200
| Project E | ET2 | Larry | 88 | 160 | 160 | 160 | 160 | 160 | 160 | 960 | 80 | 80 | 80 | 80 | 80 | 80 | 480 | 14080 | 14080 | 14080 | 14080 | 14080 | 14080 | 84480 | 7040 | 7040 | 7040 | 7040 | 7040 | 7040 | 42240
| Project E | ET2 | Stanley | 50 | 10 | 10 | 10 | 10 | 10 | 10 | 60 | 12 | 12 | 12 | 12 | 12 | 12 | 72 | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | 600 | 600 | 600 | 600 | 600 | 600 | 3600
| Project E | ET2 | George | 60 | 20 | 20 | 20 | 20 | 20 | 20 | 120 | 25 | 25 | 25 | 25 | 25 | 25 | 150 | 1200 | 1200 | 1200 | 1200 | 1200 | 1200 | 7200 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 | 9000

## Sheet2
| Values |  |  | Values
Resource | Sum of Total Budget hours | Sum of Total Actual hours | Resource | Sum of Total Budget hours | Sum of Total Actual hours | variance | %
Crystal | 900 | 900 | Crystal | 900 | 900 | 0
Erica | 960 | 900 | Erica | 960 | 900 | -60 | -6.25%
Gail | 930 | 1026 | Gail | 930 | 1026 | 96 | 10.32%
George | 960 | 1200 | George | 960 | 1200 | 240 | 25%
Inigo | 960 | 660 | Inigo | 960 | 660 | -300 | -31.25%
Jenny | 960 | 1020 | Jenny | 960 | 1020 | 60 | 6.25%
Jim | 960 | 1050 | Jim | 960 | 1050 | 90 | 9.375%
Larry | 960 | 480 | Larry | 960 | 480 | -480 | -50%
Monique | 960 | 1200 | Monique | 960 | 1200 | 240 | 25%
Sarah | 960 | 1020 | Sarah | 960 | 1020 | 60 | 6.25%
Sondra | 960 | 960 | Sondra | 960 | 960 | 0 | 0%
Stanley | 720 | 864 | Stanley | 720 | 864 | 144 | 20%
Tom | 960 | 990 | Tom | 960 | 990 | 30 | 3.125%
Grand Total | 12150 | 12270 | Grand Total | 12150 | 12270 | 120 | 0.9877%
Erica, Inigo, Larry seem to be under budget and least utilized on the project.
Monique & George are 25% over the budget
Because of offsetting, overall the actual hours are very close to the budget
| Values |  |  | Values
Project | Sum of Total Budgetted Cost | Sum of total Actual cost | Project | Sum of Total Budgetted Cost | Sum of total Actual cost | variance | %
Project A | 153600 | 168150 | Project A | 153600 | 168150 | 14550 | 9.473%
Project B | 131100 | 135600 | Project B | 131100 | 135600 | 4500 | 3.432%
Project C | 216000 | 243300 | Project C | 216000 | 243300 | 27300 | 12.64%
Project D | 291000 | 271500 | Project D | 291000 | 271500 | -19500 | -6.701%
Project E | 174480 | 138240 | Project E | 174480 | 138240 | -36240 | -20.77%
Grand Total | 966180 | 956790 | Grand Total | 966180 | 956790 | -9390 | -0.9719%
•Whereas the Actual Cost of doing Project B is the lowest, and the Actual Cost of doing Project D is the highest.
•Actual Project cost for D & E were less by 7% and 21%.
•Total Actual cost to execute all 5 Projects, was less by 1% than what was budgeted
•Indicates that the budgeting was done well and execution even better.
One reason could be that the project team was able to complete the project with fewer resources than initially estimated.
Another reason could be that the team was able to negotiate better prices for materials or services required for the project.
A possible Risk - unexpected risk, events or changes in project scope that would have increased costs may not have occurred.
| Values |  |  | Values
Project | Sum of Total Budgetted Cost | Sum of total Actual cost | Project | Sum of Total Budgetted Cost | Sum of total Actual cost | variance | percent
Project A | 153600 | 168150 | Project A | 153600 | 168150 | 14550 | 9.473%
Project B | 131100 | 135600 | Project B | 131100 | 135600 | 4500 | 3.432%
Project C | 216000 | 243300 | Project C | 216000 | 243300 | 27300 | 12.64%
Project D | 291000 | 271500 | Project D | 291000 | 271500 | -19500 | -6.701%
Project E | 174480 | 138240 | Project E | 174480 | 138240 | -36240 | -20.77%
Grand Total | 966180 | 956790 | Grand Total | 966180 | 956790 | -9390 | -0.9719%
for Project A, B, C - reasons include unexpected expenses, changes in scope, delays, and unforeseen circumstances.
For Project D & E, reasons could include efficient resource utilization, effective cost management,
completing the project ahead of schedule, and favorable economic conditions.
Futher anaysis is required to know the reasons for the cost savings to identify any best practices that can be applied to future projects.
There can be various reasons why a project's actual cost is lower than its budgeted cost. Some common reasons include efficient resource utilization, effective cost management, completing the project ahead of schedule, and favorable economic conditions. It's important to analyze the reasons for the cost savings to identify any best practices that can be applied to future projects.